PoLi Oracle

Build Action Plan

Post-IEU Handover  |  23 June 2026

# Context

IntellectEU has completed delivery of the PoLi Oracle Daml contract layer across four sprints under SOW #USGTC 20260010. All sprints have been accepted. The contract logic is functional on DevNet with full end-to-end verification confirmed via the Bruno API collection on 22 June 2026.

This action plan covers the work required on the Stratalink side to take the delivered contracts into a production-ready PoLi Oracle service. Items are grouped into five phases, ordered by dependency. Phase 0 must be completed before any coding begins.

Progress as of 13 July 2026. Phase 3 is CLOSED, per the Phase 3 Closure Record (PoLi-P3-CLOSE-01, 13 July 2026). Items 01, 03 and 04 are built and proven on-ledger; item 02 is closed by descope. Phase 0 is complete. Phase 1 is complete on the local sandbox, with items 01 and 02 still sandbox-only and unverified against DevNet. Phase 2 items 01 to 04 are complete. Phase 2 item 05, STRATA AI scoring, is now BLOCKED rather than merely outstanding, because the five-factor STRATA composite does not map onto the four score fields the contract carries.

Three paths were exercised end to end on the sandbox on 12 July: ATTEST for BTC/USD, producing a PoLiAttestation with ten live venues named; REJECT for SHIB/USD, producing a RejectedAttestationRequest carrying a coded, parseable reason; and PARK for BUIDL/USD, producing nothing on-ledger and a durable record of why. The parked store survives process death and does not re-decide.

Two workstreams now sit ahead of further building. PoLi-VER-01, a 24-test verification of the delivered contract, of which one test has been run. And PoLi-CR-01 v2.3, a four-field change request to IntellectEU which should not be sent until that verification is complete. Both are described in the new Phase 5 below.

# Phase 0: Prerequisites (before any code)

These items unblock everything else. They require no application code and can be completed today.

| # | Action Item | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| 01 | Generate SECP256K1 keypair for DevNet | Rob | COMPLETE | OpenSSL command: generate private key, extract DER-encoded compressed public key as hex string (see Appendix A). Store private key securely. This is NOT the IEU test key visible in the Bruno screenshots. |
| 02 | Generate separate SECP256K1 keypair for MainNet | Rob | COMPLETE | Separate keypair for production. Private key must never be shared. MainNet public key registered via CreateOrchestrator when ready. |
| 03 | Confirm repo has been cloned from IEU | Rob | COMPLETE | Action item from Sprint 2. David Martins walked through the setup. Confirm you have the repo and can build the Daml project locally. |
| 04 | Confirm Docker container delivered in Sprint 4 | Rob | COMPLETE | Anastasiia (infrastructure) was preparing this. If delivered, you can run the Canton sandbox locally via Docker instead of hitting DevNet during development. |
| 05 | Confirm CO party IDs for DevNet and MainNet | Rob | COMPLETE | Resolved during Sprint 3 demo (identical except display name). Confirm you have both recorded. Format: compliance-officer::1220... |
| 06 | Extract Bruno environment variables | Rob | COMPLETE | Record the defaultUrl, operator_partyId, consumer_partyId, complianceOfficer_partyId, orchestratorTemplateId, attestationRequestTemplateId, poliAttestationTemplateId, and interfaceAttestationTemplateId from the Bruno collection. These are the contract addresses your service will call. |

# Phase 1: Authentication and Orchestrator Registration

Replicate the first three Bruno calls programmatically. This phase proves your service can talk to the Canton Ledger API and register your real keypair.

| # | Action Item | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| 01 | Build Keycloak token management module | Rob | SANDBOX ONLY | Replicate Auth-Operator call. Handle 300s access token expiry and 1800s refresh token lifecycle automatically. Endpoint: keycloak.catalyst.stratalink.ai, realm: catalyst-canton-nonprod, client_id: stratalink-devnet. Sandbox-proven only: the equivalent flow was validated against the local sandbox at localhost:7575 using a local shared-secret token. Return to test the live Keycloak token lifecycle against the catalyst-canton-nonprod realm on DevNet before marking full complete. |
| 02 | Register DevNet Orchestrator with real public key | Rob | SANDBOX ONLY | Submit CreateOrchestrator command with your real SECP256K1 public key (from Phase 0). This replaces the test key. One-time setup per environment. Sandbox-proven only: CreateOrchestrator was validated on the local sandbox and returned a successful transaction. Return to register the Orchestrator on DevNet with the real public key before marking full complete. |
| 03 | Verify Orchestrator registration via FetchOrchestrator | Rob | COMPLETE | Confirm the active contract on-ledger contains your public key and the correct operator and compliance officer party IDs. |
| 04 | Choose language and project structure | Rob | COMPLETE | Python (cryptography library) or Node.js (ethers.js or noble-secp256k1). Python recommended for SECP256K1 signing ergonomics. Decide before Phase 2. |

# Phase 2: Signing and Attestation Processing

This is the core build. Your service must construct the canonical payload, sign it with SECP256K1, and submit scored attestations to the ledger.

| # | Action Item | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| 01 | Implement canonical payload construction | Rob | COMPLETE | Pipe-delimited concatenated string. DecimalType format: value 0.95 becomes value:95, range:2, string "952". Rating included in signed payload. Refer to PoLi Attestation Data Structure Spec v1.4. Confirmed 11 July 2026. The canonical payload is 16 pipe-delimited fields in the exact order defined by the VerifyValidity choice. The rating is derived client-side via poLiScoreToRating rather than taken as free input, since the contract recomputes it. |
| 02 | Implement SECP256K1 payload signing | Rob | COMPLETE | Sign the canonical payload string with your private key. Output must be hex-encoded signature compatible with the on-ledger VerifyValidity logic. Confirmed 11 July 2026. Two encoding defects were found and fixed. First, the signature must be DER-encoded (ASN.1 SEQUENCE beginning 0x30); the @noble/secp256k1 v2.3 toBytes("der") call returns the raw compact form and must not be used. Second, Daml sha256 takes a hex-encoded byte string and hashes the decoded bytes, so sha256 (toHex payload) is SHA-256 over the raw UTF-8 bytes of the payload, not over the hex characters. |
| 03 | Build ProcessAttestationRequest submission | Rob | COMPLETE | Replicate the Bruno ProcessAttestationRequest call with real signed payloads. Start with hardcoded test scores (value: 80, range: 2) to isolate signing from scoring. |
| 04 | End-to-end verification test on DevNet | Rob | COMPLETE | Run the full flow: auth, fetch pending request, sign, submit, verify. The VerifyAttestationValidity call must return ttl: true, signature: true, overall_valid: true. If signature fails, the issue is in payload construction or key format. |
| 05 | Integrate STRATA AI scoring engine | Rob | BLOCKED | Replace hardcoded test scores with live venue data. This connects the PoLi Oracle to the STRATA AI computation layer. Four sub-scores: poliScore, depthScore, spreadScore, balanceScore. Status changed to BLOCKED on 12 July 2026. Not deferred by choice: the integration cannot be built correctly against the contract as it stands. STRATA does not compute four scores. It computes a weighted five-factor composite: Data Quality 30 per cent, Resilience 20 per cent, Execution Integrity 20 per cent, Fragmentation 15 per cent, Regime Stability 15 per cent. The contract carries four fields, so the mapping is a flattening: poLiScore takes the composite, depthScore takes Resilience, spreadScore takes Execution Integrity, balanceScore takes Fragmentation. Data Quality and Regime Stability, together 45 per cent of the composite weight, have nowhere to go and are not represented on the attestation at all. The range field is also now understood. It carries stability_score scaled 0 to 10, derived from the composite's own variance. The stub sends a fixed range of 2 on every attestation, which means every attestation issued to date asserts a confidence level that was never computed. It is a signed field. STRATA exposes GET /api/analytics/l3f/snapshot/:symbol, returning the full factor breakdown plus a contributing_venues array with per-venue depth, spread and weight. Latency is 18ms cached, sub-200ms cold. Insufficient data returns HTTP 503. There is no model version identifier. Building against a four-field structure Stratalink is about to ask IntellectEU to change would be wasted work. This item follows the contract change, it does not precede it. See PoLi-CR-01 v2.3. |

# Phase 3: Consumer and Polling Infrastructure

Your service needs to detect incoming AttestationRequest contracts and process them automatically rather than relying on manual Bruno calls.

| # | Action Item | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| 01 | Build AttestationRequest polling or event listener | Rob | COMPLETE | Two approaches: poll /v2/state/active-contracts with template filter (as Bruno does), or use the /v2/updates/transaction-tree stream for real-time event-driven processing. Complete 11 July 2026. Polling chosen over the transaction-tree stream, deliberately: it mirrors the Bruno collection exactly, so any discrepancy is attributable to the adapter rather than to a difference in detection mechanism. The streaming upgrade replaces only the detection layer and can be made later without touching the processing path. The blocker was a package-name versus package-hash asymmetry. The JSON Ledger API returns template IDs in package-hash form but only accepts the package-name form as a query filter. Do not round-trip a returned templateId back into a filter. The active-contracts endpoint paginates. fetchActiveRequests drains every page. Missing a request is a correctness failure, not a performance one. |
| 02 | Implement consumer registration flow | Rob | DESCOPED | Consumer onboarding. Auth-Consumer call, then exercise RequestAttestation. May be manual initially; automate later. Recommended for descope, 12 July 2026. The Oracle Adapter is the OPERATOR, not the consumer. Consumer registration is a test harness for producing AttestationRequest contracts to process, and Bruno already does that job. If consumer onboarding is needed as a product capability it belongs in the RCL or TILT, not in the Oracle Adapter. Retain the item only if a specific need emerges. |
| 03 | Build attestation lifecycle management | Rob | COMPLETE | Track contract state: pending requests, processed attestations, rejected requests. Handle edge cases such as duplicate requests and stale TTL. Complete 12 July 2026, and it is not what this item originally described. It turned out to be reconciliation, not persistence. VER-21 established that the ledger enforces single-processing. A second ProcessRequest against an already-processed AttestationRequest returns CONTRACT_NOT_FOUND, errorCategory 11, grpcCodeValue 5. ProcessRequest archives the request, so duplicate attestation is not possible whatever the adapter's memory believes. The in-flight set was therefore guarding against something that cannot happen, and a persisted failed set would not have solved the problem it was built for: it records what the adapter believed, and after a timeout the adapter's belief is precisely what is in doubt. Only the ledger can settle it. Both sets have been removed. The adapter reconstructs its state from the ledger on every cycle. Note definite_answer: false in that error. The ledger is not saying whether your command had an effect, only that the contract is gone. If a command landed and its response was lost, an attestation exists that the Oracle has no record of issuing. That is a bookkeeping failure, not a duplicate risk, and CONTRACT_NOT_FOUND is therefore a reconcile signal, never a retry signal and never a shrug. Exactly one fact cannot be reconstructed from the ledger: which requests the Oracle deliberately did not answer, and why. A parked request is indistinguishable on-ledger from one the poller has not reached. That, and only that, is persisted, in data/parked.json. It is a BACKLOG, not a dead-letter box: every parked request will be reprocessed once the contract gains observationType. On stale TTL, referenced in the original note: there is no staleness guard, deliberately. A request outstanding for an hour is attested with a FRESH score. STRATA cannot produce a request-time score in any case, since the buffer is a 60-minute rolling window. A guard would be the Oracle refusing to answer a question it can answer, in service of one nobody can answer, and would substitute the Oracle's judgment for the consumer's on a threshold the consumer owns. |
| 04 | Implement RejectAttestationRequest flow | Rob | COMPLETE | Not all requests should be honoured. Build the rejection path with reason logging, matching the Bruno RejectAttestationRequest call. Complete and proven on-ledger 12 July 2026. The first coded rejection Stratalink has written to a ledger: POLI-REJ-001¦Asset pair not within DACT coverage universe¦SHIB/USD¦2026-07-12T01:23:18Z The governing principle, codified in POLI-REJ-STD-1.0: the Oracle rejects only when it cannot form a view. An attestation is a statement about the market; a rejection is a statement about Stratalink. Coverage failure is ours, data sparsity is the market's. Insufficient_data is therefore ATTESTED with a None rating, never rejected: it is a legitimate Status in the contract, and rejecting on it would discard the Oracle's most valuable output, namely the finding that a venue reports a pair as liquid and the book does not support the claim. Four codes: POLI-REJ-001 outside DACT coverage, 002 consumer not authorised, 003 calculation not implemented, 004 malformed request. Evaluated in code order, coverage first. 002 and 003 are dormant: the entitlement model has not been specified, and the contract errors on non-PoLiScore calculation types before the adapter sees them. The reason string is four pipe-delimited fields: code, human clause, subject, observed-at. Code first so the RCL can parse without natural-language processing; clause second so the raw ledger record is legible without the codebook. The contract asserts NOTHING about reason and will accept a null. The taxonomy is enforced entirely in the adapter and nothing on-ledger will tell you if it drifts. Where the adapter meets a condition the codebook does not cover, it must not invent a code and must not process the request. It parks it. An unactioned request is recoverable; a wrong rejection on the ledger is permanent. |

# Phase 4: Production Readiness

Items required before MainNet deployment. Some can proceed in parallel with Phases 2 and 3.

| # | Action Item | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| 01 | Externalise rating table | Rob | NOT STARTED | Known technical debt from IEU handover. Rating thresholds are currently hardcoded in the Daml contracts. Move to on-ledger or off-ledger configuration so rating changes do not require contract redeployment. |
| 02 | Implement production key management (HSM) | Rob | DEFERRED | PEM file storage acceptable for DevNet. MainNet requires HSM or managed key service (AWS KMS, Azure Key Vault, or Google Cloud KMS). Scope options before MainNet launch. Note added 12 July 2026. The AWS KMS option touches billing account 472151629788. Flag, do not action without confirmation. |
| 03 | Register MainNet Orchestrator | Rob | NOT STARTED | One-time CreateOrchestrator on MainNet with production keypair. Validator credentials issued via Catalyst platform. Treat as sensitive. |
| 04 | Build monitoring and alerting | Rob | NOT STARTED | Token expiry monitoring, attestation throughput, signature verification failure alerts, ledger offset tracking. |
| 05 | Documentation and runbook | Rob | NOT STARTED | Operational runbook covering key rotation, incident response, and environment-specific configuration. Update the five project documents to reflect final implementation. |

# Phase 5: Verification and Change Control

This phase did not exist in the original plan. It was added on 12 July 2026 because building the adapter surfaced findings in the delivered contract that must be settled before further building is worthwhile, and because those findings must be taken to IntellectEU once, grounded in evidence, rather than in instalments of design opinion.

Every finding to date came from reading the Daml, not from running it. That is the reason for item 01. Nothing is sent to IntellectEU until it is complete.

| # | Action Item | Owner | Status | Notes |
| --- | --- | --- | --- | --- |
| 01 | Run PoLi-VER-01 contract verification | Rob | COMPLETE | COMPLETE, 12 July 2026. All 24 tests were run against the delivered contract. Four findings resulted, recorded in the Phase 3 Closure Record and in the standalone VER-08 and VER-16 finding papers. Findings 1 and 2 are HIGH and are properties of the same choice. Finding 1: key rotation destroys the entire attestation record, because the attestation carries no record of which key signed it and the verifier reads whatever key is registered now. Finding 2: only the consumer can verify an attestation; the Platform Operator that issued it and the Compliance Officer the contract explicitly models are both refused with DAML_AUTHORIZATION_ERROR. Finding 3 is a disclosure question on the Compliance Officer. Finding 4 is a low-severity rating guard defect. Consumer isolation was tested and HOLDS, which was the catastrophic-failure case. VER-21 established that the ledger enforces single-processing, which reshaped Phase 3 item 03. Section 4 of the plan is the one that matters and it has not been touched. VerifyAttestationValidity has only ever returned true. Stratalink's entire proposition rests on the claim that a PoLi attestation is verifiable. If the verifier cannot be made to return false, it is not verifying anything, and every attestation issued carries a guarantee that has never been shown to have teeth. VER-05 is the heavy one: alter each of the sixteen signed fields in turn and confirm the signature breaks each time. The field list came from reading VerifyValidity and has never been confirmed. Any field that can be changed without breaking the signature is not actually signed, whatever the Daml appears to say. VER-16 will settle the compliance officer disclosure question empirically. VER-19 will settle signingKeyId, and may make that question unnecessary altogether. Do not adjust a test to make it pass. A plan where everything passes has probably not tested anything. |
| 02 | Issue PoLi-CR-01 v2.3 to IntellectEU | Rob | REFRAMED | REFRAMED, 13 July 2026. Item 01 is complete and the verification changed what this document should be. PoLi-CR-01 v2.3 as drafted groups defects together with change requests. It must be split before it is sent. Findings 1 and 2 are non-conformities against the Amendment A4 Acceptance Criteria and are pursued under Amendment A8 as a defect notice, at IntellectEU cost. Findings 3 and 4, together with the four provenance fields, remain a change request. See Phase 6. The four fields proposed for PoLiAttestation, all appended to the signed payload, are observationType, venueSet, modelVersion and requestCreatedAt. They are one argument, not four asks. The attestation records a number but not the circumstances under which the number was produced: whether the depth was observed or derived, which venues informed it, which model computed it, and how long the request had been waiting. The cost of the gap is measurable. Eight of thirty-four covered symbols are currently unattestable, comprising the entire tokenized securities class: ACRED, BCSPX, BENJI, BIB01, BUIDL, OUSG, USDY, VBILL. Stratalink observes these assets and can score them. It will not attest them while doing so would present synthetic depth as observed depth. The document also raises, without yet asking for, the five-factor flattening described in Phase 2 item 05. Copy Paula Costa. If this generates work it lands in her delivery scope, and it is scope beyond SOW #USGTC 20260010. |
| 03 | Replace DACT coverage config with a live query | Rob | NOT STARTED | config/coverage.json is transcribed by hand from the DACT coverage table as at 11 July 2026: 26 venues, 34 symbols, all USD-quoted. It will drift. The CoverageProvider interface does not change when this is replaced. Only the source does. That was the point of the abstraction. Note that the config IS the policy. A typo in it is a policy change, and DactCoverageProvider throws on a missing file rather than defaulting to empty coverage, because empty coverage would reject every request as outside the universe. |
| 04 | Specify the consumer entitlement model | Rob | NOT STARTED | POLI-REJ-002, consumer not authorised, is dormant. PermissiveAuthorisationProvider authorises everyone. The model determining which consumers may request attestation for which pairs has not been specified. It is a commercial and regulatory question rather than a technical one, and it bears on the RCL. The AuthorisationProvider interface exists so the answer slots in without a refactor. |

# Phase 6: Contractual Position

This phase was added on 13 July 2026 following a review of SOW #USGTC 20260010 (£38,660) as signed. It exists because two of the four PoLi-VER-01 findings are properties of the delivered contract rather than requests for new functionality, and the route by which they are pursued materially changes what Stratalink is owed.

The previously open question was whether the fifteen-day warranty window had closed. That question is now largely displaced. Amendment A8 carries no expiry.

| Provision | Position |
| --- | --- |
| Warranty (SOW) | Fifteen days from delivery, on a commercially reasonable efforts standard. The weaker route, and likely lapsed. |
| GTC Clause 8 | Deemed acceptance ten business days after receipt. Cuts against Stratalink. Countered by the fact that Amendment A4 is a special term agreed between the Parties and prevails over the GTC under GTC Clause 1. |
| Amendment A4 | Acceptance Criteria. Requires at (c) an Attestation contract containing a valid cryptographic signature, and at (d) successful consumer exercise of the on-ledger verification choice. |
| Amendment A8 | Outcome-Based Delivery and Remediation. Overrides the commercially reasonable efforts standard for the PoLi Daml Contract Codebase specifically. IntellectEU is obliged to deliver in a condition satisfying Amendment A4. Three remediation attempts, then material breach and termination without penalty. No expiry attached. |
| Expiration Date | 23 July 2026. |

Findings 1 and 2 will be pursued under Amendment A8 against the Amendment A4 Acceptance Criteria, not under the warranty clause. Finding 1 carries the stronger argument: an attestation whose signature ceases to verify after a routine operational event does not satisfy Amendment A4(c) in any durable sense. Finding 2 is weaker against A4 read narrowly, because the consumer can verify, which is what A4(d) requires on its face. It remains a defect in fitness for the purpose the SOW states.

Defects must be communicated separately from change requests. Grouping them invites the vendor to treat defect remediation as chargeable scope.

Stratalink will not modify the Daml itself. Whoever’s package hash is on MainNet is the party attesting. A self-modification would transfer ownership of the attestation layer from IntellectEU to Stratalink, materially weaken the regulatory position, and place any future merge conflict in the signed payload structure.

| # | Action Item | Notes |
| --- | --- | --- |
| 01 | Establish the delivery date of the PoLi Daml Contract Codebase | Now supporting evidence rather than the load-bearing question. Evidence hierarchy: GitLab tags and release markers, formal handover emails, sprint demo records including Fireflies transcripts, invoicing records. NOT STARTED. |
| 02 | Split PoLi-CR-01 v2.3 into a defect notice and a change request | Findings 1 and 2 become a written notice of non-conformity under Amendment A8. Findings 3 and 4 and the four provenance fields remain a change request. NOT STARTED. |
| 03 | Issue the defect notice to IntellectEU | Bruno Almeida, Head of Digital Assets, as primary strategic contact. Copy Paula Costa, Delivery Manager. Consider issuing before the Expiration Date of 23 July 2026. NOT STARTED. |
| 04 | Issue the change request to IntellectEU | Follows the defect notice, separately. Copy Paula Costa. This is scope beyond SOW #USGTC 20260010. HELD pending item 02. |

# Appendix A: SECP256K1 Keypair Generation

Run the following commands to generate your keypair. The private key stays on your machine. The public key hex string is what gets registered in the Orchestrator contract.

Step 1: Generate private key

openssl ecparam -name secp256k1 -genkey -noout -out poli_po_private_devnet.pem

Step 2: Extract DER-encoded compressed public key as hex string

openssl ec -in poli_po_private_devnet.pem -pubout -conv_form compressed -outform DER 2>/dev/null | xxd -p | tr -d '\n'

This outputs the full DER-encoded compressed SECP256K1 public key as a lowercase hex string. This is what goes into the publicKey field on the CreateOrchestrator command. Format confirmed by Joao Gaspar as DA.Crypto.Text.PublicKeyHex (DER format).

Step 3: Verify the output length

The hex string should be 112 characters (56 bytes DER-encoded). The underlying compressed public key is 33 bytes (66 hex characters) wrapped in a 23-byte DER header.

Step 4: Repeat for MainNet with a separate keypair

openssl ecparam -name secp256k1 -genkey -noout -out poli_po_private_mainnet.pem

Store both private keys securely. Never commit them to version control. Never share them with any third party including IntellectEU.

# Appendix B: Bruno Environment Variables to Extract

Open the Bruno collection settings and record the following variables from the DevNet environment. These values are required for your service configuration.

| Variable | Where Used |
| --- | --- |
| defaultUrl | Base URL for all Canton Ledger API calls |
| operator_partyId | Operator party ID for actAs and command submission |
| consumer_partyId | Consumer party ID for attestation requests |
| complianceOfficer_partyId | CO party ID for Orchestrator creation |
| orchestratorTemplateId | Template ID for Orchestrator contracts |
| orchestratorContractId | Active Orchestrator contract ID (changes per creation) |
| attestationRequestTemplateId | Template ID for AttestationRequest contracts |
| poliAttestationTemplateId | Template ID for PoLiAttestation contracts |
| interfaceAttestationTemplateId | Template ID for VerifyValidity interface |
| ledgerEnd | Current ledger offset (used in activeAtOffset) |

# Appendix C: Sensitive Items Register

The following items are classified as sensitive and must be handled with appropriate care.

| Item | Classification | Handling |
| --- | --- | --- |
| SECP256K1 private keys (DevNet and MainNet) | Critical | Never shared, never committed to VCS |
| Keycloak client_secret | Sensitive | Stored in environment variables only |
| Canton validator credentials (Party ID format: stratalink-validator-1::1220...) | Sensitive | Issued via Catalyst platform. Do not output full credential strings. |
| AWS billing account 472151629788 | Financial infrastructure | Flag but do not modify without explicit confirmation |
| finance@stratalink.ai alias | Financial infrastructure | Flag but do not modify without explicit confirmation |