TILT PRODUCTION INTEGRATION Canton Integration Work Plan Stratalink Labs Ltd ¦ Based on TILT Strip-List v1.0 and DAML Codebase Review ¦ 12 June 2026 Version 1.0 ¦ June 2026 ¦ CONFIDENTIAL

1.  Purpose and Scope

This document defines the remaining integration work required to connect TILT to the Canton/DAML codebase delivered by IntellectEU under SOW #USGTC 20260010. It supersedes the sprint sequencing in the TILT Strip-List v1.0 (11 May 2026), which was written before the DAML contracts were finalised. The work plan anchors to the signed-off DAML codebase reviewed on 12 June 2026 and the Attestation Data Structure v1.2 (2 June 2026).

The objective is a production-grade TILT that acts as the PoLi Oracle: consuming the DACT feed, computing canonical PoLi-STD-1.1 attestations, signing them with SECP256K1, and submitting them to the Canton ledger via the JSON Ledger API. The five-step SOW Amendment A4 acceptance criteria are the definition of done.

2.  Baseline - What Is Confirmed as of 12 June 2026

DAML CODEBASE - REVIEWED AND SIGNED OFF 12 JUNE 2026 Attestation.daml and Orchestrator.daml reviewed against v1.2 spec. Verification choice: soft fail, overall_valid boolean, no status field mutation, archive as separate choice. Rating signing convention: optional None show rating correctly implemented. Canonical payload: 16 tokens, pipe delimited, correct field order, createdAt excluded, DecimalType value/range pairs confirmed. SECP256K1 with ECDSA used throughout - not Ed25519. DevNet deployment authorised.

| DAML Contracts | Attestation.daml, Orchestrator.daml, Types.daml - reviewed and signed off 12 June 2026 |
| --- | --- |
| Signing Algorithm | SECP256K1 with ECDSA (secp256k1WithEcdsaOnly). Ed25519 references in Strip-List v1.0 and Data Structure spec are superseded |
| Canonical Payload | 16-token pipe-delimited string per v1.2 spec. Field order locked. createdAt excluded. DecimalType value/range encoding confirmed |
| Party IDs - DevNet | Operator: stratalink-validator-1::1220ec7d... ¦ CO: compliance-officer::1220ec7d... |
| Party IDs - MainNet | Operator: stratalink-validator-1::1220cd06... ¦ CO: compliance-officer::1220cd06... |
| Verification Design | Soft fail. overall_valid = ttl && isValid. No error thrown by default. strict_mode optional. Archive on STALE as separate choice |
| Rating Convention | Sign as 'A' not 'Some A'. Sign as 'None' when rating is None or status is insufficient_data |
| DevNet Status | Deployment in progress - Joao Gaspar authorised 12 June 2026. Monday demo target |
| Bruno API Collection | Sprint 2 snapshot - confirm delivery to repo at today's Sprint 4 meeting |
| TILT Codebase | Hosted on Replit (Node.js/Express + React/Vite, TypeScript). Repository: Morpheus1305/LIS-TILT-V1 on GitHub |
| Spec Version | Attestation Data Structure v1.2 (2 June 2026). Note: spec references Ed25519 in places - v1.3 update required (Rob action) |

3.  What Needs to Be Built - Oracle Adapter

THE ORACLE ADAPTER DOES NOT EXIST YET Per the TILT Strip-List v1.0, the entire Oracle Adapter is a NEW BUILD. Zero lines exist in the current TILT codebase. This is the largest and most critical body of work between now and SOW acceptance. The canonicaliser is the single most important module - any byte-level divergence between Stratalink signing and IntellectEU DAML verification breaks the attestation chain.

| # | Module | What it does | Dependency | Priority |
| --- | --- | --- | --- | --- |
| 01 | poli-scoring.ts | PoLi-STD-1.1 three-component scoring engine. Depth (50%), Spread (35%), Balance (15%). Evidence ladder. Calibration parameters for BTC, ETH, SOL. Status and rating derivation per v1.2 rating table. | None - standalone | P1 - BUILD NOW |
| 02 | poli-canonicaliser.ts | Canonical 16-token pipe-delimited serialiser per v1.2 spec. DecimalType trailing-zero stripping. SHA-256 hash of UTF-8 encoded string (no trailing newline). MUST be verified with fixture-based unit tests before any signing. | poli-scoring.ts | P1 - BUILD NOW |
| 03 | canonicalisation.test.ts | Fixture-based byte-level unit tests. Minimum 20 fixtures covering: normal attestation, insufficient_data, max score, zero score, all rating tiers, mid-precision timestamps, None rating. Joint sign-off with IntellectEU mandatory. | poli-canonicaliser.ts | P1 - BUILD NOW |
| 04 | poli-signer.ts | SECP256K1 signing layer. Sprints 1-3: locally generated keypair (PEM on disk). Sprint 4/production: swap to AWS KMS or CloudHSM. Exposes sign(payload: string): signature and getPublicKey(): PublicKeyHex interfaces. | poli-canonicaliser.ts | P1 - BUILD NOW |
| 05 | canton-keystore.ts | Manages local PEM keypair for DevNet. Stores signingKeyId. Abstracts key source so AWS KMS swap in Sprint 4 is a single-module change. Registers public key with Orchestrator contract on initialisation via UpdatePublicKey choice. | poli-signer.ts | P1 - BUILD NOW |
| 06 | canton-client.ts | Canton JSON Ledger API client. Polls for AttestationRequest contract creations. Exercises ProcessRequest choice on Orchestrator with signed CalculationPayload. Handles Keycloak JWT auth. Wires to DevNet validator endpoint. | Bruno API collection | P1 - BLOCKED on Bruno |
| 07 | poli-attestation-builder.ts | End-to-end pipeline: LISSnapshot from DACT buffer -> PoLiSnapshot -> CanonicalPayload -> SECP256K1 signature -> ProcessRequest submission. Owns 5-minute TTL calculation. Handles insufficient_data path (all scores zero, rating None). | canton-client.ts | P2 - after 06 |
| 08 | poli-attestation.ts (route) | Internal API surface for operator console. GET /api/poli/attestations/recent (last 20). GET /api/poli/attestations/:txId. Canton submission status. Signing key panel data. | poli-attestation-builder.ts | P3 - after 07 |

4.  TILT Strip-List v1.0 - Current Status

The strip list was written in May 2026 against v1.1 of the spec and planned four sprints from scratch. We are now in Sprint 4 of the SOW with the DAML contracts finalised. The table below reconciles strip list actions against current status.

| Ref | Strip List Action | Notes | Category | Status |
| --- | --- | --- | --- | --- |
| SL-01 | DELETE: Old PoLi engine (14 files, ~4,800 LOC) | poliEngine.ts, poliVenueEvidence.ts, poliMarketIntegrityEvidence.ts and related. Old A-F rating model, pre-STD-1.1. | Code cleanup | CONFIRM |
| SL-02 | DELETE: Identity Intelligence module (9 files, ~1,500 LOC) | Arkham client, MM integrity, regulatory surveillance, identity alerts. Not on Canton MVP critical path. | Code cleanup | CONFIRM |
| SL-03 | DELETE: CCP Margin Console (5 files, ~4,100 LOC) | Clearing-house-focused product. Not part of Canton MVP scope. | Code cleanup | CONFIRM |
| SL-04 | DELETE: Liquidity Tape consumer surface (4 files) | tape.tsx, tape.ts, tapeStore.ts. DACT ingestion preserved at L1; consumer UI not needed for MVP. | Code cleanup | CONFIRM |
| SL-05 | DELETE: RCL / ADGM regulatory dashboard (3 files) | rclMock.ts, rcl.ts, RegulatoryAdgmView.tsx. Synthetic mock data has no place in production. | Code cleanup | CONFIRM |
| SL-06 | DELETE: Consumer marketing surface (11 files, ~2,800 LOC) | landing.tsx, documentation.tsx, scorecard.tsx, lis-debug.tsx etc. Not operator-console-facing. | Code cleanup | CONFIRM |
| SL-07 | PARK: Alert system (5 files, ~900 LOC) | alerts.ts, alert-service.ts, divergence-detector.ts. Move to tilt-future-alerts branch. Do not delete. | Park | CONFIRM |
| SL-08 | REPLACE: L5F engine with poli-scoring.ts | analytics-layer.ts (L5F DQ/Res/Frag/EI/Reg) replaced with PoLi-STD-1.1 three-component engine. New file: server/services/poli-scoring.ts. | Core build | BUILD |
| SL-09 | REPLACE: analytics-l5f.ts route with /api/poli/snapshot | Old L5F endpoint replaced with canonical PoLiSnapshot endpoint serving PoLi-STD-1.1 output. | Core build | BUILD |
| SL-10 | HARDEN: Synthetic fallback handling on all CEX relays | Non-AMM venues must drop rather than substitute on outage. AMM venues (Uniswap, GMX, Curve) keep synthetic provenance tag. | Hardening | CONFIRM |
| SL-11 | CUT: canton-relay.ts as a venue source | Canton is the destination not a source venue. Reading attestation depth back as a venue breaks PoLi-STD-1.1 Principle 3. | Code cleanup | CONFIRM |
| SL-12 | REFACTOR: tilt-terminal.tsx to operator console | Strip L5F UI. Add: live attestation panel, signing key panel, Canton submission status, venue health panel, insufficient-data alert. | UI refactor | BUILD |
| SL-13 | REFACTOR: platform-tabs.tsx and dashboard-header.tsx | Collapse to operator-only navigation. Remove Identity and consumer-platform nav links. | UI refactor | BUILD |
| SL-14 | HARDEN: Authentication (server/auth.ts) | Fixed OTP (291305) kept as scaffolding. Production access gated by Cloudflare Access IP allowlist on operator subdomain. | Hardening | DEFERRED |
| SL-15 | NEW: Oracle Adapter (6 modules) | See Section 3. poli-canonicaliser.ts is the most critical. canyon-client.ts blocked on Bruno API collection. | Core build | BUILD |
| SL-16 | UPDATE: Ed25519 references throughout TILT | Strip-List v1.0 and Data Structure spec v1.2 reference Ed25519. DAML uses secp256k1WithEcdsaOnly. All TILT signing code must use SECP256K1. | Spec alignment | BUILD |

5.  Delivery Sequence

SEQUENCING PRINCIPLE The canonicaliser and its fixture tests must be built and verified before the signer, and the signer before the Canton client. Any byte-level divergence between poli-canonicaliser.ts and the DAML verifyAttestation choice reconstruction breaks the entire attestation chain. Build in order, test at each boundary.

| Phase | What | Detail | Gate |
| --- | --- | --- | --- |
| Phase 1 | Codebase cleanup | Execute SL-01 through SL-07 and SL-10, SL-11, SL-13. Create tilt-canton-mvp branch. Delete the dead code. Repo must build cleanly with no orphaned imports after cleanup. | Repo builds clean. No orphaned import errors. |
| Phase 2 | PoLi scoring engine | Build poli-scoring.ts implementing PoLi-STD-1.1 three-component engine (Depth 50%, Spread 35%, Balance 15%). Evidence ladder. Status derivation. Rating table per v1.2 Section 4. Calibration parameters for BTC, ETH, SOL. Run against live DACT buffer data to validate calibration before pinning. | Valid PoLiSnapshot JSON to stdout matching v1.2 schema. |
| Phase 3 | Canonicaliser and fixture tests | Build poli-canonicaliser.ts: 16-token pipe-delimited serialiser, DecimalType trailing-zero stripping, SHA-256 hash. Build canonicalisation.test.ts with minimum 20 fixtures. MANDATORY: send fixture set to Joao Gaspar for joint sign-off before Phase 4 begins. Include edge cases: insufficient_data, max score, zero score, all rating tiers, None rating. | Joao Gaspar joint sign-off on fixture set. Zero byte-level divergence. |
| Phase 4 | Signing layer and keystore | Build poli-signer.ts using SECP256K1 (not Ed25519). Locally generated keypair for DevNet. Build canton-keystore.ts: PEM management, signingKeyId registry, UpdatePublicKey registration against Orchestrator contract. Key rotation logic ready for AWS KMS swap in production. | Signed payload verifiable against DAML secp256k1WithEcdsaOnly. |
| Phase 5 | Canton client | Build canton-client.ts using Bruno API collection. Poll for AttestationRequest contract creations on DevNet. Exercise ProcessRequest choice. Keycloak JWT auth. Wire to DevNet party IDs. Test end-to-end: AttestationRequest -> signed Attestation -> verifyAttestation passes. | End-to-end flow passes on Canton DevNet. All five SOW Amendment A4 criteria demonstrable. |
| Phase 6 | Attestation builder and operator console | Build poli-attestation-builder.ts pipeline. Build poli-attestation.ts route. Refactor tilt-terminal.tsx to operator console with all five panels: live attestations, signing key, Canton submission status, venue health, insufficient-data alert. | Operator console live. All five panels functional. |
| Phase 7 | Production hardening | AWS KMS or CloudHSM swap in poli-signer.ts. Cloudflare Access IP allowlist on operator subdomain. Calibration parameter version pinning. Run full Amendment A4 acceptance suite three times on DevNet. Capture evidence pack. | Production-grade signing. Acceptance evidence pack complete. MainNet-ready. |

6.  Dependencies and Blockers

| # | Dependency | Owner | Required by | Status |
| --- | --- | --- | --- | --- |
| D-01 | Bruno API collection - DAML template IDs, choice names, Ledger API schema, transaction payload format, Keycloak JWT auth config, party hosting config. Required to build canton-client.ts. | Bruno Almeida / IntellectEU | Phase 5 | CONFIRM |
| D-02 | DevNet deployment confirmation from Joao Gaspar - required before end-to-end testing can begin. | Joao Gaspar / IntellectEU | Phase 5 | DONE |
| D-03 | Canonicalisation fixture set joint sign-off with Joao Gaspar. Send 20+ fixtures; receive written confirmation that DAML verifyAttestation reconstructs identically. | Rob / Joao Gaspar | Phase 3 | BUILD |
| D-04 | SECP256K1 keypair generation for DevNet. Locally generated asymmetric keypair. Private key PEM on disk for Sprints 1-3. Public key registered to Orchestrator via UpdatePublicKey choice. | Rob McDermott | Phase 4 | BUILD |
| D-05 | AWS KMS vs AWS CloudHSM production signing decision. Required before Phase 7 key swap. DevNet phases proceed with local PEM; this decision gates MainNet only. | Rob McDermott | Phase 7 | DEFERRED |
| D-06 | Calibration parameters for BTC, ETH, SOL (depth target, spread target). First-principles estimates in poli-scoring.ts must be validated against live DACT buffer data and pinned in Layer 0 governance config before acceptance testing. | Rob McDermott | Phase 2 | BUILD |
| D-07 | Attestation Data Structure spec v1.3 update. Replace Ed25519 references with SECP256K1. Rob action - no IEU dependency. | Rob McDermott | Phase 1 | BUILD |
| D-08 | MainNet Party IDs already confirmed. MainNet CO Party ID received from Joao 12 June 2026. All four Party IDs logged in Canton Infrastructure and Credential Store v1.1. | Joao Gaspar / IntellectEU | Phase 7 | DONE |

7.  Key Risks

| Risk | Area | Detail | Mitigation |
| --- | --- | --- | --- |
| R-01 | Canonicaliser mismatch | Any byte-level divergence between poli-canonicaliser.ts and DAML verifyAttestation reconstruction breaks the attestation chain silently. This is the highest-probability failure mode. | Phase 3 fixture tests with joint IEU sign-off mandatory before Phase 4. 20+ fixtures including all edge cases. |
| R-02 | Bruno collection not delivered | canton-client.ts cannot be finalised without the Bruno API collection. If it does not arrive before Phase 5, the Canton integration must be built to an assumed interface and reworked. | Chase at Sprint 4 meeting today. Phases 1-4 are Bruno-independent and can proceed in parallel. |
| R-03 | SECP256K1 implementation error | Ed25519 and SECP256K1 are different algorithms with different signing mechanics. Using the wrong Node.js library or wrong key format produces signatures that pass locally but fail DAML secp256k1WithEcdsaOnly verification. | Build fixture test that round-trips a signature through the DAML verifier before Phase 5 integration. |
| R-04 | Synthetic fallback leakage | A CEX outage (Bybit geo-block, OKX rate-limit) triggers a synthetic fallback code path that gets included in a signed attestation. This is a production integrity failure that breaks PoLi-STD-1.1 Principle 3. | Enforce in poli-scoring.ts: non-AMM venues with transport=synthetic are dropped from evidence set. CI test asserts no signed attestation with non-AMM synthetic provenance. |
| R-05 | SOW expiry timeline | SOW expires 23 July 2026. The 15 business day acceptance window opens on final source code delivery from IntellectEU. Phases 1-4 are within Stratalink's control. Phase 5 onwards depends on DevNet stability. | Phases 1-4 targeted for completion before end of June. Acceptance testing window must open by 1 July at latest to allow buffer. |

8.  Immediate Actions - This Week

| # | Action | Owner | By |
| --- | --- | --- | --- |
| W-01 | Update Attestation Data Structure spec to v1.3 - replace Ed25519 with SECP256K1 throughout. | Rob McDermott | Today |
| W-02 | Confirm Bruno API collection delivery at Sprint 4 meeting today. If not delivered, escalate to Bruno Almeida directly. | Rob McDermott | Today |
| W-03 | Create tilt-canton-mvp feature branch on Replit/GitHub. All subsequent work lands here until Amendment A4 acceptance is signed off. | Rob McDermott | Today |
| W-04 | Generate SECP256K1 keypair for DevNet. Store private key PEM securely (1Password). Note public key for Orchestrator UpdatePublicKey registration. | Rob McDermott | This week |
| W-05 | Begin poli-scoring.ts build. Three-component engine, evidence ladder, rating table per v1.2 Section 4. Run against live DACT buffer to validate calibration. | Rob McDermott | This week |
| W-06 | Begin poli-canonicaliser.ts build in parallel with scoring engine. First fixture: the worked example from v1.2 spec Section 6 (Joao's reference JSON, 2 June 2026). | Rob McDermott | This week |

v1.0 - 12 June 2026: Document created. Anchored to DAML codebase review 12 June 2026, Attestation Data Structure v1.2, and TILT Strip-List v1.0. Supersedes sprint sequencing in Strip-List v1.0.